## Sample Sprint Plan
This is an 'example' of what a Sprint Plan for a given Sprint might look like. It is organized to show an executive summary in the form of EPICs and point summaries at the top, with details and a formula based summing function that tracks progress over the course of the sprint. Note that there are comments explaining some of the items in various cells. A comment is notated by a red corner - hover over it to see the description. Reference the next tab for a simple Glossary of Agile¦Sprint Related Terminology.
Sprint 'Name or Number' - May 2011
| Total Points Attempted | 21 | Sprint Effort Remaining
| Total Points Completed | 5 | 76.19%
| Points Remaining: | 16
EPICS - This is a List of Big Projects or Categories that you work on. Your stories should each support one of your team's epics.
Lead Generation - Do you have a goal of 1,000 leads per month? What different activities help you reach that goal? Break them into stories.
Sales Enablement - Are you creating collateral, doing training, something else?
Q2 Event - Do you have a big event you work on? Break it up into workable chunks …
PR & Social Media Engagement - Is there any push or ongoing interaction with the community of influencers and followers you care about?
Enter your categories / EPICs in this list to help summarize what you are working on.
Marketer | Working Days In Sprint | Working Days | Potential Points | Points Committed | Comments
Name | Month of May = 21 Business Days, Less any days off | 21 | 63 | N/A
Marketer 1 | 19 Days, VACA: 2 Days off | 19 | 57 | 61 | **Red Flag - Overcommitted**
Marketer 2 | No time off planned | 21 | 63 | 62
Marketer 3 | 1 day off 5/27 | 20 | 60 | 55 | **Could take on some of Marketer 2s work. Collaborate.
Marketer 4 | 1/2 Day Dentist | 20.5 | 61.5 | 60
Priority | EPIC & Stories | Success criteria | Points (Numeric Values Only) | Owner(s) | Points Completed (Numeric Values Only) | Status (conditional formatting)
EPIC | Sample Epic - Your 'Big Category'
1 | Sample Story - A story should be a smaller, bite-sized chunk of work that can be written from the perspective of the end consumer of the deliverable. "As a Insert Your Company Name sales person, I need a Insert Your Sales Need, so that I can Insert What this Thing Will Enable." If you cannot answer the question of why you are doing it or define what success looks like - maybe you shouldn't be doing it ... | Sample Success Criteria: New Email Template with Proposal Live & Sales Trained to Use. Less one off requests for this collateral piece. | 3 | Marketer 1 | 2 | In Progress
EPIC | Lead Generation
1 | Blog Management ¦ As a HubSpot Marketer, I want to ensure we have 3 blog posts per day that can generate 5,000 organic leads per month. -Create Blog Calendar -Monitor content velocity -Edit & publish blogs | 90 Blogs Published & 5,000 Leads Generated | 8 | Marketer 1 |  | Not Started
2 | Blog Content Creation ¦ As a HubSpot Marketer, I need to contribute 3 blog articles per month that each generate 1,500 page views or more. -Brainstorm Topics -Write posts -Promote in Social Media | 3 Blogs Written, 4,500 toal page views or more generated | 3 | Marketer 1 | 3 | Complete!
EPIC | Sales Enablement & Product Content
2 | HubSpot FAQs Home Base ¦ As a HubSpot customer I have questions that aren't covered on classical 'product' pages - make it easy for me to find the answers and make it easy for sales to share them with me. -Define structure & content types for FAQ -Define 'home' in navigation for FAQ -Define first 5-6 articles for FAQ -Build Skeleton (search faqs and objections - from IMC and sale managers) | FAQ Page launched with 5-6 FAQs | 3 | Marketer 1 |  | Not Started
3 | HubSpot FAQ Article 1: How Long Till I See Results? ¦ As a HubSpot prospect, I want to understand what I can expect in terms of results in traffic, leads and customers from the time that I start using HubSpot. -Draft Page -Get PM/Sales Input -Publish & Link to FAQ Page | Article Published & Promoted to Sales, 100 Page Views in Month 1 with positive anecdotal evidence | 3 | Marketer 2 |  | Not Started
1 | WhitePaper: Inbound Marketing & Integration ¦ As a HubSpot Marketer, I want a meaty ebook / white paper on the concepts of Inbound Marketing and the value of a single integrated inbound marketing solution. (TIMEBOXED AT 3 POINTS) -Develop TOC (Table of Contents) -Get Team Input & Start writing | First Draft WP Available by End of May | 3 | Marketer 2 | 1 | In Progress
4 | Platform Training ¦ As a HubSpot Sales Rep, I need to better understand the new Platform value & capabilities, so I need small group training with Q&A. -Finish Content -CoLead 6 Small Group Training Sessions -Follow up with Q&A Post Training | Sales team starts to demo the Platform. | 3 | Marketer 3 | 2 | In Progress
5 | Sales Digest ¦ As a HubSpotter, there are so many new features, programs and info that it is hard to keep up with it all. Create & publish a weekly digest email that highlights all the important changes to product, collateral, competition and more. -1 Sales Digest / Week | Enablement material sent. | 4 | Marketer 2 | 1 | In Progress
EPIC | Q2 Event / Trade Show / Lead Gen
1 | Master Planing ¦ As a Marketer, I want everyone to be on the same page for our event and know where to go to get information. -Update & track team activities to plan -Recruit additional talent & manage bi-monthly meetings | Sample Success Criteria: Team planning page live & bi-monthly meetings in progress. (this is an activity more than result - sometimes you have those) | 3 | Marketer 1 | 1 | In Progress
2 | HUGS 2011 Agenda ¦ As a HubSpot Customer, I want to know what's going to be happening at HUGS so I can decide if I want to get an Early Bird Ticket. -Tracks Defined & Named -Event Description Updated -Brainstormed List of Potential Presos Ready to Rationalize -Keynote Big Name Locked | Sample Success Criteria: 50% Agenda available, able to publish/promote keynote. | 5 | Marketer 1 |  | Not Started
EPIC | PR & Social Media Engagement
2 | Social Media Monitoring ¦ As a Marketer, I want to increase social media followers by 5% so that I have greater reach and can engage with more potential customers / existing customers. -engage in one new social network -monitor social outlets twice daily via social media tool -find retweetable content to could drive sharing & tweet/share | Sample Success Criteria: Increase Social Media Reach by 5% | 8 | Shared 2 points per week per marketer | 2 | In Progress
1 | Prepare for June Launch ¦ As a Marketer, I want to have a list of stellar bloggers and journalists to reach out to when we unveil exciting thing ABC. -Determine what is 'newsworthy" & draft messaging -Shortlist outlets that might find the item of interest -Offer sneak preview & to write guest blog post or interview | Sample Success Criteria: List of 20 or more identified & outreach team ready to engage. | 5 | Marketer 3 |  | Not Started
Note on A26: kknipp: Prioritization. First prioritize by EPIC and then prioritize the stories within the EPIC. This makes discussions about shifting priorities much easier.
Note on C8: kknipp: This is a formula that SUMS all of the story points budgeted 'Points Committed' column D.
Note on C9: kknipp: Formula that sums all the 'points completed' in column F.
Note on C10: kknipp: Total Points Attempted minus completed gives you a status of where you stant. The percentage value is at right.
Note on C26: kknipp: Success criteria should be a measurable outcome of the task - whether data or qualitative … what does success look like? Marketers can be much more autonomous if everyone knows what the goal looks like.
Note on D19: kknipp: 'Proper' agile planning does not use 'time' to define how many points you have, but this is on liberty that some of HubSpot marketing has taken so we can more effectively estimate our workload. In this case, we assign 3 points to a day with the base assumption that each point equates to a chunk of 3 hours of work.
Note on F21: kknipp: This marketer should find some way to defer / shrink or share some of the work on his/her plate to ensure success.
Note on G26: kknipp: The cells in this column have conditional formatting which means that they change color & text based on another cell. In this case - points completed. This gives you a quick view of what's going well or NOT going.

## Agile Glossary
A Marketer's Simplified Agile / Scrum Glossary
Term | Definition
Team Backlog | A prioritized list of high level requirements. This list is a 'living document' that ebbs and flows over time as stories are added, completed and should be monitored by the Product Owner (PO) / Team Lead.
Sprint | A time period (typically 2–4 weeks) in which work occurs on a set of backlog items that the Team has committed.
Sprint Backlog | A prioritized list of tasks to be completed during the sprint.
Epic | A large effort split up into multiple related user stories. If you have a very big project, it might be an 'Epic' that extends across various sprints, but each Epic should be broken down into manageable chunks.
User Story | A detailed description of a task with the stakeholders in mind. See the agile presentation for the 'anatomy' of a proper user story.
Sprint Burn Down | Daily progress chart for a Sprint over the sprint’s length. Not included in this spreadsheet and not a 'must have', but a nice visual representation of progress. See screen shot below.
Sample Sprint Burn Down
Impediment/Blocker | Anything that prevents a team member from performing work as efficiently as possible. Daily standup aims to uncover blockers and get team input on resolution.
Planning Poker | The team estimates effort for the stories in the backlog. The PO uses estimates to prioritize & forecast stories based on velocity, the pace the team typically works.
Point Scale | Point system, used to describe task difficulty, without assigning actual hours. HubSpot uses the Fibonacci sequence (1,2,3,5,8…). Some HubSpot Marketing teams do use 'hour increments' as shown in this sample to simplify planning. For the 'Evangelism Team' (the team this sample is modeled after) assigns 1 point to every 3 hours with 3 points per working day. This provides the team a proxy effort level and helps most effectively estimate effort.
Success Criteria | The exit-criteria to determine if a task is complete. This concept should be familiar to anyone using MBOs (management by objective) principles - simply completing a task may not be enough, success is defined by some outcome or result in many cases. Having a clear definition of success enables team members to function independently on individual but interdependent stories.