## Slide 1
PERT Diagram
Task | Description | Blocked by | Duration | Start date | Finish date
A | Description of task A |  | 10 | 0 | 10
B | Description of task B |  | 7 | 0 | 7
C | Description of task C | A | 5 | 10 | 15
D | Description of task D | C | 3 | 15 | 18
E | Description of task E | D | 2 | 18 | 20
F | Description of task F | B,E | 1 | 20 | 21
G | Description of task G | F,H | 14 | 21 | 35
H | Description of task H | D | 0 | 20 | 21
Data Table

## Slide 2
PERT Diagram - Instructions
Definition
The PERT Diagram consists of a graphical representation of the different stages that make up a project, connected by the tasks that need to be completed to accomplish it.
Steps | Description
1 | Create a list of the different tasks in a project.
2 | Estimate the duration of each task, as well as their start and finish dates.
3 | Arrange the tasks and establish dependencies between them.
4 | Create the visual representation.
Steps to create a PERT diagram
Task
Stage
Duration
Start Date
Finish Date

## Slide 3
PERT Diagram
Graphical Representation
A
10
B
7
C
5
D
3
E
2
H
0
F
14
B’
G
14
H’
Start
End
0
0 | 0
1
0 | 10
3
10 | 15
4
15 | 18
6
20 | 21
2
0 | 7
5
18 | 20
7
20 | 21
8
21 | 35