## How to Use This Template
How to Use This Template
1. List the activities you will carry out in your project over the course of a year. The schedule is divided into four quarterly periods, but you can divide it into bi-monthly periods, for example.
2. Next, use different colors to highlight the cells where each activity will take place. This provides a helpful visual aid.
3. Indicate the start and end dates for each activity within the corresponding month. This will add greater precision to your schedule.
4. Leave the months in which no activities will take place as blank.
5. You can make your schedule as detailed as you need it to be, depending on your specific requirements.

## Schedule
SCHEDULE
| Activites |  | Year: 2023
|  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
|  |  | January | February | March | April | May | June | July | August | September | October | November | December
Period 1 | 1 | Implementation of CRM in the company (free version). | Q1 January: (Jan 3rd)
| 2 | Contact Migration | Q1 January: (Jan 12 - 21)
| 3 | CRM training for team members. (Logistics managed by the sales team leader). | Q1 January: (Jan 12 - 21)
| 4 | Monthly CRM performance evaluation. | Q1 February: (Feb 25th)
| 5 | Quarterly CRM performance evaluation. (Purchase decision based on budget). | Q1 March: (Mar 25th)
Period 2 | 6 | bar: Q2 April to Q2 June
7 | bar: Q2 April to Q2 June
8 | bar: Q2 April to Q2 June
9 | bar: Q2 April to Q2 June
10 | bar: Q2 April to Q2 June
Period 3 | 11 | bar: Q3 July to Q3 September
12 | bar: Q3 July to Q3 September
13 | bar: Q3 July to Q3 September
14 | bar: Q3 July to Q3 September
15 | bar: Q3 July to Q3 September
Period 4 | 16 | bar: Q4 October to Q4 December
17 | bar: Q4 October to Q4 December
18 | bar: Q4 October to Q4 December
19 | bar: Q4 October to Q4 December
20 | bar: Q4 October to Q4 December